## Time Standards
LED MIRROR — ASSEMBLY TIME STANDARDS
Blue cells are editable inputs. All times in minutes.
STEP # | OPERATION | STD TIME (min) | BEST CASE (min) | WORST CASE (min) | NOTES
LANE 1 — FRAME
F1 | Cut 2x4s to rough length | 3 | 2 | 5 | Per frame; batch cutting saves setup time
F2 | Mill profiles — standard segments | 5 | 4 | 8 | Router table; all identical segments
F3 | Mill electronics pocket segment | 7 | 5 | 10 | Dedicated fixture; one per frame
F4 | Miter & glue assembly | 8 | 6 | 14 | Jig essential — do not freehand
F5 | Clamp & cure wait | 0.5 | 0.5 | 0.5 | Active time only; glue cures passively
F6 | Sand & finish pass | 4 | 3 | 6 | Light pass before final assembly
F7 | Frame QC — square & joints | 2 | 1 | 3 | Check square, pocket dims, joint tightness
↳ LANE 1 — FRAME SUBTOTAL
LANE 2 — MIRRORS
M1 | Batch cut 12x12 sheet → 4x 6x6 | 4 | 3 | 6 | Wet saw; amortized per sheet (÷4 for per unit)
M2 | Edge inspection & clean | 1.5 | 1 | 3 | Check for chips; wipe clean
M3 | Custom design cut (if applicable) | 6 | 4 | 12 | Laser or CNC; skip for blank units
M4 | Mirror QC — clarity & edges | 1.5 | 1 | 2 | Inspect both panels before assembly
↳ LANE 2 — MIRRORS SUBTOTAL
LANE 3A — LED STRIP PREP
E1 | Incoming test (full strip pre-cut) | 2 | 1.5 | 3 | Bench PSU + test harness; reject bad strips
E2 | Cut strip to spec length | 1.5 | 1 | 2 | Score and snap on cut line
E3 | Solder connector — VIN pad | 3 | 2 | 5 | Hakko iron; fine tip; flux first
E4 | Solder connector — GND pad | 3 | 2 | 5 | Inspect joint under loupe
E5 | Solder connector — DATA pad | 3 | 2 | 5 | Most critical joint — verify continuity
E6 | Post-solder power-on test | 2 | 1.5 | 3 | All LEDs must fire before proceeding
E7 | Seat strip into 3D printed spacer | 2 | 1.5 | 3 | Press fit; check alignment
↳ LANE 3A — LED STRIP PREP SUBTOTAL
LANE 3B — CONTROLLER PREP
C1 | Receive & inspect controller | 1.5 | 1 | 3 | Check for physical damage; ESD precautions
C2 | Flash firmware (per unit, batched) | 3 | 2 | 5 | Pi jig; batch 5-10 at once to amortize setup
C3 | Solder required pads/through-hole | 5 | 3.5 | 8 | Per controller BOM; inspect all joints
C4 | Controller function test | 2 | 1.5 | 3 | Power on, verify comms & output
C5 | Seat controller into 3D housing | 1.5 | 1 | 2 | Press fit; secure if needed
↳ LANE 3B — CONTROLLER PREP SUBTOTAL
FINAL ASSEMBLY
A1 | Kit check — all sub-assemblies present | 1.5 | 1 | 2 | Traveler card sign-off before starting
A2 | Install controller housing into pocket | 3 | 2 | 4 | Secure; verify cable routing path
A3 | Lay mirror #1 into milled channels | 2 | 1.5 | 3 | Handle with suction cups; no fingerprints
A4 | Seat LED strip assembly | 2 | 1.5 | 3 | Align to mirror edge; route cable
A5 | Lay mirror #2 | 2 | 1.5 | 3 | Verify alignment and spacing
A6 | Install backing | 3 | 2 | 4 | Fasten; check no rattles
A7 | Cable management & connector routing | 3 | 2 | 5 | All cables secured; connector accessible
A8 | Final power-on QC | 3 | 2 | 5 | Full function test; LED uniformity check
A9 | Visual inspection | 2 | 1.5 | 3 | Mirror alignment; no scratches or marks
A10 | Box & pack | 3 | 2 | 5 | Protective packaging; label; ready to ship
↳ FINAL ASSEMBLY SUBTOTAL
TOTAL — PER UNIT (STD / BEST / WORST)
TOTAL — PER UNIT (hours)

## Unit Calculator
LED MIRROR — UNIT TIME CALCULATOR & DASHBOARD
Adjust batch size and custom mirror flag. All times pull live from Time Standards sheet.
INPUTS
| Batch Size (units per run) | 10 | Number of units built per production batch
| Orders per Day | 1 | Target daily output
| Include Custom Mirror Cut? | 1 | 1 = Yes (custom design), 0 = No (blank unit)
| Operator Efficiency Factor | 85% | 1.0 = perfect; 0.85 = realistic for trained operator
| Hourly Labor Rate ($/hr) | 25 | Fully-loaded operator cost
PER-UNIT TIME SUMMARY
| LANE / OPERATION | STD (min) | BEST (min) | WORST (min) | STD (hrs) | LABOR COST ($)
Frame
Mirrors
LED Strip Prep
Controller Prep
Final Assembly
SUBTOTAL (raw)
ADJUSTED (÷ efficiency factor)
BATCH & THROUGHPUT METRICS
Total Batch Time — STD (hrs)
Total Batch Time — BEST (hrs)
Total Batch Time — WORST (hrs)
Units per 8-hr Day (STD)
Labor Cost per Unit (STD)
Labor Cost per Batch (STD)
Custom Mirror Upcharge (min)
BOTTLENECK IDENTIFIER
Frame
Mirrors
LED Strip
Controller
Final Assembly

## Batch Planner
LED MIRROR — WEEKLY BATCH PLANNER
Plan your weekly production sessions by operation. Inputs pull from Unit Calculator.
WEEKLY DEMAND INPUTS
| Orders per Week | 7 | Standard week at 1/day
| Working Days per Week | 5 | Available production days
| Hours Available/Day | 6 | Net productive hours (not 8 — be realistic)
RECOMMENDED BATCH SCHEDULE
| OPERATION | UNITS/BATCH | SESSIONS/WK | HRS/SESSION | TOTAL HRS/WK | NOTES
| Frame Build |  |  |  |  | Cut & mill all frame segments in one pass per batch
| Mirror Cutting |  |  |  |  | Cut full sheets; store 6x6 blanks; custom cut per order
| LED Strip Prep |  |  |  |  | Solder station; batch for efficiency — do full week at once
| Controller Prep |  |  |  |  | Flash in trays; solder same session
| Final Assembly |  |  |  |  | Pull from sub-assembly bins; daily or every 2 days
TOTAL PRODUCTION HRS / WEEK
CAPACITY CHECK
| Available Hrs/Week |  |  |  |  | Working days × hrs/day
| Required Hrs/Week |  |  |  |  | From batch schedule above
| Utilization Rate |  |  |  |  | Target 70–85% for sustainable pace
| Headroom (hrs/week) |  |  |  |  | Positive = capacity available